## Sheet1
Meeting Minutes
Purpose: | Setup
Meeting Title: | Kickoff & Git Workflow Setup
Date: | 2026-05-08
Time: | 10:00 - 12:00
Location: | Discord
Facilitator: | Kiệt
Note Taker: | Kiệt
Attendees: | Kiệt, Lâm, Thắng
Discussion Points
Topic | Discussion Summary
Steam Deconstruction | Phân tích DOM trang Steam. Chốt chia 3 khối (Header, Main, Footer). Chạy task Desktop & Mobile song song cho kịp tiến độ.
Git Workflow & Tool | Chốt xài GitKraken. Thắng tạo repo gốc. Chia nhánh cá nhân (Lius/..., Thang/Dev, Lam/Dev).
Commit & PR Rules | Thống nhất chỉ Push & tạo PR khi file (giấy, Figma, code) đã final 100%. Không push file dở dang/file rác lên Git.
Decisions Made
Decision | Rationale
Vẽ Block Layout tĩnh | Dễ hình dung khung container, tiện bóc tách thẻ div sau này.
Chỉ Push bản Final | Cây Git đang chia nhiều nhánh, làm vậy để tránh đụng code (conflict) khi merge vào
Action Items
Action Item | Owner | Due Date | Status
Init Repo & PR setup | Thắng | 2026-05-08 | Done
Paper Blocklayout - Desktop | Kiệt | 2026-06-08 | In Progress
Paper Blocklayout - Mobile | Thắng | 2026-06-08 | In Progress